## INSTRUCTIONS
CPSC 3720 - Service Release Plan
PART 1: ESTIMATE SHEET
Step 1: List High Level Stories/Epics Listing and Discussion
In Column A, list all high level user stories (use the "As a ___, ….. , so I can…" format) that are relevant to your service
As a team, go through the stories and talk about what it would take to build the story; put your notes into Column B
If you think the story needs some research or prototyping to determine the right approach; include this in the notes
Step 2: Rank all stories from Lowest Complexity to Highest Complexity
Each Team Member will take a turn, rotating in the same order until all stories are ranked from low to high
During a Team Member's turn they may either:
* Place (Cut or Ctrl+X) one story from the pool into the Low to High column C OR
* Re order one story that's already been placed in the Low to High Column C
Once all stories have been ranked, allow each team member to take one more turn to re-order any additional items
Step 3: Assign Fibnoacci points
Each Team Member will take a turn, rotating in the same order until all stories are pointed
During a Team Member's turn they may either:
* Place (Cut or Ctrl+X) one fibonacci card (point) into the "Estimate" column OR
* Re order one Fibonacci card that's already been placed in the "Estimate" column
Placing a Fibonacci card adjacent to a User Story indicates the estimate of that Story AND ALL STORIES ABOVE IT.
Team members should start with the lowest Fibonacci number they can for the ordered stories, and work their way up sequentially.
PART 2: PLANNING SHEET
Step 1: Move Stories and Estimates
Move your list of stories and estimates from the Estimate Sheet to Columns B and C in the Planning Sheet
Number Each Story in Column A
Step 2: Discuss and Assign Business Priority and to the Stories
For each story Discuss its priority; in Column D, rank from 1-5 with 5 being the highest priority
Put your notes justifying the priority in Column E
Step 3: Discuss and Determine Dependencies
Review your stories from the perspective of what must be completed before another story can begin.
List those dependent stories (can be multiple) in Column F with any notes in Column G
PART 3: INITIAL RELEASE PLAN SHEET
Assumptions
You develop your services with 2 week sprints (assume so for Sprint 0 but you may adjust in Step 2)
Historically, your team is averaging 5 SPs per person per 2 week sprint
Sprint 0 starts on Jan 2 2023
Step 1: Layout your initial sprint calendar
Determine total velocity per sprint for your team based on the assumption above (per person velocity)
Given total estimates, map out how many sprints you need after Sprint 0 (sprint 0 would not count towards the "burn-down")
Identify the dates of each 2 week sprint in Row 1
Step 2: List tasks for Sprint 0
What do you need in place before you can start your release?
List these items in Column A under Sprint 0
Are any of these so big that you may need to adjust your Sprint 1 start date (if 2 weeks is not enough for Sprint 0)? Consider and adjust as needed.
Step 3: Assign Velocity per sprint
On row 2, assign the expected velocity per sprint (not for Sprint 0); in most cases this should match the number you came up with in Step 1 above; however, think about major holidays adjust the velocity as you deem appropriate
If you have less total SPs given holidays, add additional sprints to get you back to the required total SPs
Step 4: Assign Stories to Sprints
Stories should be mapped to each sprint considering priority and dependencies
You cannot put stories in a sprint that will total more than the entire sprint velocity
You may have to spread stories across multiple sprints if they are too big
Add sprints as needed if your arrangement has stories that cannot fit properly in the plan you had in Step 3
DONE!!!

## Estimate Sheet
Your Service Stories - Comprehensive list of stories for your service | Tasks/Notes re: Story | Complexity Order of Stories (Rows in Order) | Estimate (Fibonacci)
As a CSR, I would like access to all tickets submitted by customers so that I can resolve customer issues | Should be very easy, just getting all of the database entries | Lowest complexity | 1
As a customer, I would like to get details about a specific ticket I have submitted so that I can ensure the ticket details are correct | Can be accomplished by getting a single ticket by its ticketID, which maps to database entry key | - | 1
As a CSR, I would like to get details about a specific ticket so that I can avoid accidentally affecting other tickets | Can be accomplished by getting a single ticket by its ticketID, which maps to database entry key | - | 1
As a CSR, I would like to delete ticket responses so that I can remove inaccurate follow-up information | Can be accomplished with a response's responseID, which just requires getting a single ticket and finding the correct array item | - | 2
As a CSR, I would like to delete tickets so that I can prevent old tickets from being confused with new tickets | Should use filters to delete all tickets with certain qualities Should be able to delete in bulk or individually | - | 2
As a customer, I would like to get a listing of the tickets I have submitted so that I can check the status of them | Checks the tickets submitted under a customer's name or email, very easy once ticket filtering is complete | - | 3
As a customer, I would like to see all closed tickets that I have submitted so I can reopen tickets if necessary | Customer needs to be able to see closed tickets in case of having to reopening a ticket that has been submitted previously Can likely leverage other methods | - | 3
As a customer, I would like to close tickets so that I can avoid wasting CSRs' time with unnecessary requests | Can be accomplished by updating ticket status | - | 8
As a customer, I would like to re-open tickets so that I do not have to create a new ticket for a request I submitted previously | Can be accomplished by updating ticket status | - | 8
As a customer, I would like to update tickets so that I can provide the most accurate and up-to-date information for CSRs | May be useful to have update methods that perform single and bulk operations Input validation also necessary | - | 13
As a CSR, I would like to update tickets so that I can correct ticket information if necessary | Will require input validation Likely similar requirements to customers' epic | - | 13
As a CSR, I would like to add responses to a ticket so that I can inform customers about the status of their requests | Will require input validation | - | 13
As a customer, I would like to communicate with a CSR to resolve an issue listed in a ticket | Requires customer to be able to submit responses to their ticket Will require input validation | - | 13
As a CSR, I would like to filter tickets so that I can view specific tickets according to my needs | Should include filters for as many ticket fields as possible (customer info, timestamps, account/order info, etc.) | - | 34
As a customer, I would like to submit a ticket to get an issue resolved | Requires input validation (includes correct fields, doesn't include extraneous fields, sanitized input, etc.) Customer needs to be able to narrow down their issue type and provide relevant account/order details | Highest complexity | 34

## Planning Sheet
Story Number | Your Service Stories - Comprehensive list of stories for your service | Fib. Estimate | Business Priority Ranking | Priority Notes | Dependent Stories | Dependency Notes
1 | As a CSR, I would like access to all tickets submitted by customers so that I can resolve customer issues | 1 | 5 | CSRs cannot access any ticket information without this story | N/A | Not dependent on any other epic
2 | As a customer, I would like to get details about a specific ticket I have submitted so that I can ensure the ticket details are correct | 1 | 5 | Customers need to be able to see that their ticket was created successfully, and ensure any details are correct | N/A
3 | As a CSR, I would like to get details about a specific ticket so that I can avoid accidentally affecting other tickets | 1 | 5 | CSRs need to be able to limit the scope of their operations to one ticket at a time to avoid interfering with other support requests | N/A
4 | As a CSR, I would like to delete ticket responses so that I can remove inaccurate follow-up information | 2 | 2 | CSRs could just as easily create a new response that explains a mistake, but this feature is still useful | 3
5 | As a CSR, I would like to delete tickets so that I can prevent old tickets from being confused with new tickets | 2 | 1 | Deleting old data is only a "nice-to-have" | 3
6 | As a customer, I would like to get a listing of the tickets I have submitted so that I can check the status of them | 3 | 4 | Customers need to be able to view their support requests, but doing so is not necessarily as important as being able to create requests | 14
7 | As a customer, I would like to see all closed tickets that I have submitted so I can reopen tickets if necessary | 3 | 2 | Customers could just as easily create new tickets, it would be unorganized and unideal but this feature is not strictly necessary | 14
8 | As a customer, I would like to close tickets so that I can avoid wasting CSRs' time with unnecessary requests | 8 | 2 | In many cases, CSRs would be able to tell if a customer's issue is resolved if the details provided in the ticket are no longer consistent with the customer's data | 2023-02-15
9 | As a customer, I would like to re-open tickets so that I do not have to create a new ticket for a request I submitted previously | 8 | 2 | Customers could just as easily create new tickets, it would be unorganized and unideal but this feature is not strictly necessary | 2023-02-15
10 | As a customer, I would like to update tickets so that I can provide the most accurate and up-to-date information for CSRs | 13 | 3 | Customers could just as easily provide new information with a new ticket response | 2023-02-15
11 | As a CSR, I would like to update tickets so that I can correct ticket information if necessary | 13 | 4 | It's important for CSRs to be able to correct ticket information in case another CSR has to take over a ticket | 2023-03-15
12 | As a CSR, I would like to add responses to a ticket so that I can inform customers about the status of their requests | 13 | 4 | CSRs should be able to communicate with customers, but not having this feature would not stop a CSR from solving some customer issues | 2023-03-11
13 | As a customer, I would like to communicate with a CSR to resolve an issue listed in a ticket | 13 | 5 | Customers should be able to communicate with CSRs in case more information is provided, but not having this feature would not stop a CSR from solving some customer issues | 2023-02-10
14 | As a CSR, I would like to filter tickets so that I can view specific tickets according to my needs | 34 | 4 | The ability to filter tickets will be crucial to implementing planned as well as future features | 1
15 | As a customer, I would like to submit a ticket to get an issue resolved | 34 | 5 | Customers cannot submit any support requests without this story | N/A

## Initial Release Plan
January 2, 2023 - January 13, 2023 | January 16, 2023 - January 27, 2023 | January 30, 2023 - February 10, 2023 | February 13, 2023 - February 24, 2023 | February 27, 2023 - March 10, 2023 | March 13, 2023 - March 24, 2023 | March 27, 2023 - April 7, 2023 | April 10, 2023 - April 21, 2023 | April 24, 2023 - May 5, 2023
NA | Est. Velocity: 20 SPs | Est. Velocity: 17 SPs | Est. Velocity: 20 SPs | Est. Velocity: 20 SP | Est. Velocity: 20 SPs | Est. Velocity: 20 SPs | Est. Velocity: 21 SPs | Est. Velocity: 11 SPs
Sprint 0 activities | Sprint 1 Stories | Sprint 2 Stories | Sprint 3 Stories | Sprint 4 Stories | Sprint 5 Stories | Sprint 6 Stories | Sprint 7 Stories | Sprint 8 Stories
Ensure each team member has access to their own AWS dev environment (Lambda, API Gateway, DynamoDB, etc.) | Story #15 - 20 SPs | Story #15 (cont.) - 14 SPs | Story #14 - 20 SPs | Story #14 (cont.) - 14 SPs |  | Story #13 - 13 SPs | Story #8 - 8 SPs | Story #7 - 3 SPs
Ensure each team member has access to a production environment |  | Story #1 - 1 SP |  | Story #10 - 3 SPs | Story #10 (cont) - 10 SPs | Story #12 - 7 SPs | Story #12 (cont) - 6 SPs | Story #9 - 8 SPs
Ensure each team member has access to their own Postman test environment (incl. mock servers) |  | Story #2 - 1 SP |  | Story #11 - 3 SPs | Story #11 (cont) - 10 SPs |  | Story #4 - 2 SPs
Ensure each team member has access to a shared Postman test environment (incl. mock servers) |  | Story #3 - 1 SP |  |  |  |  | Story #5 - 2 SPs
Ensure each team member has access to a shared GitHub repository/organization to commit changes | [6 empty] | Story #6 - 3 SPs
Create API definition (YAML)
Create mock examples for API methods in Postman